## Work Item Fields CLAIMSPROC-15
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Labels | Labels | Labels | Description | Environment | Watchers | Watchers Id | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Σ Original Estimate | Σ Remaining Estimate | Σ Time Spent | Security Level | Outward issue link (Relates) | Custom field (Issue color) | Custom field (Rank) | Custom field (Start date) | Parent | Parent key | Parent summary | Status Category | Status Category Changed
AI Infrastructure Setup | CLAIMSPROC-15 | 10861 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:39 PM | 05/Nov/25 4:39 PM | 05/Nov/25 5:29 PM |  | 11/Dec/25 12:00 AM | 0 | AI_Inventory | Pilot | Production | Set up a secure and compliant infrastructure that supports AI workloads for healthcare claims processing. This includes provisioning robust compute resources, implementing network security measures, and ensuring logging and monitoring are aligned with HIPAA compliance standards. *Acceptance Criteria:* • Infrastructure supports scalable AI workloads • Network security measures are in place and tested • Logging and monitoring are aligned with compliance requirements *Associated Controls:* - [Cyber Security (Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00009] - [TCO/ROI (Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00031] - [Model Reliability & Safety (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00029] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002c7: | 26/Nov/25 12:00 AM | 10841 | CLAIMSPROC-1 | AI Infrastructure Setup | To Do | 05/Nov/25 4:39 PM
AI Infrastructure Policy Enforcement and Access Controls | CLAIMSPROC-22 | 10875 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:39 PM | 05/Nov/25 4:39 PM | 05/Nov/25 5:30 PM |  | 27/Dec/25 12:00 AM | 0 | AI_Inventory |  | Production | Implement automated AI Infrastructure Governance policies that enforce configuration baselines, IAM least-privilege principles, and continuous compliance scans. Ensure AI workloads are deployed only on approved, compliant infrastructure. *Acceptance Criteria:* • All AI infrastructure configurations follow approved baselines • IAM permissions follow least-privilege access • Compliance scans run automatically with results reported to governance dashboards • Unauthorized deployments are blocked via policy enforcement • Infrastructure setup validated before model deployment *Associated Controls:* - [Access Control (Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00026] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002dr: | 12/Dec/25 12:00 AM | 10841 | CLAIMSPROC-1 | AI Infrastructure Setup | To Do | 05/Nov/25 4:39 PM
Third-Party AI Legal & Compliance Enforcement | CLAIMSPROC-28 | 10887 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:39 PM | 05/Nov/25 4:39 PM | 05/Nov/25 5:30 PM |  | 12/Jan/26 12:00 AM | 0 | AI_Inventory |  | Production | Implement due diligence and contract enforcement mechanisms for all third-party AI integrations. Include clauses restricting data use and enforcing confidentiality to prevent unauthorized training or leakage. *Acceptance Criteria:* • Legal contracts include explicit clauses preventing vendor retraining on customer data • Vendor compliance is verified before integration • Third-party AI providers undergo due diligence reviews • Access controls and data isolation are enforced per contract • All third-party risks are tracked in a centralized registry *Associated Controls:* - [Vendor & Third-Party Risk Management (Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00028] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002f3: | 28/Dec/25 12:00 AM | 10841 | CLAIMSPROC-1 | AI Infrastructure Setup | To Do | 05/Nov/25 4:39 PM
AI Model and Agent Inventory Registry | CLAIMSPROC-34 | 10899 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:39 PM | 05/Nov/25 4:40 PM | 05/Nov/25 5:31 PM |  | 28/Jan/26 12:00 AM | 0 | AI_Inventory | Pilot | Production | Create and enforce an AI Registry capturing all models, agents, versions, and metadata. Prevent unregistered deployments to mitigate 'Shadow AI' risk and maintain visibility into all production assets. *Acceptance Criteria:* • All AI models and agents registered before deployment • Versioning, ownership, and metadata are automatically captured • Unregistered AI assets blocked from running • Model registry integrates with CI/CD deployment gates • Shadow AI prevention validated in governance audits *Associated Controls:* - [AI Asset Inventory (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00001] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002gf: | 13/Jan/26 12:00 AM | 10841 | CLAIMSPROC-1 | AI Infrastructure Setup | To Do | 05/Nov/25 4:40 PM
AI Model Ownership and Accountability Matrix | CLAIMSPROC-40 | 10911 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:40 PM | 05/Nov/25 4:40 PM | 05/Nov/25 5:31 PM |  | 13/Feb/26 12:00 AM | 0 | AI_Inventory | Pilot | Production | Define and document primary accountable owners, secondary owners, and escalation contacts for each AI model, ensuring clear governance and accountability. *Acceptance Criteria:* • Each model has a defined Primary Accountable Owner (PAO) • RACI matrix defines secondary and escalation contacts • Ownership details stored in AI asset registry • Ownership reviewed during quarterly audits • Escalation path tested during incident simulations *Associated Controls:* - [Accountability & Ownership (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00002] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002hr: | 29/Jan/26 12:00 AM | 10841 | CLAIMSPROC-1 | AI Infrastructure Setup | To Do | 05/Nov/25 4:40 PM
Data Pipeline Setup for Claims Processing | CLAIMSPROC-46 | 10923 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:40 PM | 05/Nov/25 4:40 PM | 05/Nov/25 5:31 PM |  | 01/Mar/26 12:00 AM | 0 | AI_Inventory | Pilot | Production | Create a robust data pipeline to ingest, clean, and label healthcare data such as EDI 837 and physician notes. Ensure the pipeline integrates with existing EMR systems and maintains data privacy compliance. *Acceptance Criteria:* • Pipeline ingests all required data types • Data cleaning processes maintain compliance • Pipeline integrates with EMR systems *Associated Controls:* - [Data Privacy (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00005] - [Data Privacy (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00035] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002j3: | 14/Feb/26 12:00 AM | 10842 | CLAIMSPROC-2 | AI Data Pipeline & Labeling | To Do | 05/Nov/25 4:40 PM
AI Model Development for Claims Automation | CLAIMSPROC-53 | 10937 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:40 PM | 05/Nov/25 4:40 PM | 05/Nov/25 5:32 PM |  | 17/Mar/26 12:00 AM | 0 | AI_Inventory | Pilot | Production | Develop and test AI models designed to automate the claims adjudication process, integrating structured and unstructured data sources. Models must be scalable and adaptable to dynamic healthcare environments. *Acceptance Criteria:* • Model integrates diverse healthcare datasets • Model achieves predefined accuracy targets • Model is scalable and adaptable *Associated Controls:* - [Model Reliability & Safety (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00038] - [Human Oversight (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00039] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002kn: | 02/Mar/26 12:00 AM | 10843 | CLAIMSPROC-3 | AI Build | To Do | 05/Nov/25 4:40 PM
Validation and Testing of AI Models | CLAIMSPROC-60 | 10951 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:40 PM | 05/Nov/25 4:40 PM | 05/Nov/25 5:32 PM |  | 02/Apr/26 12:00 AM | 0 | AI_Inventory | Pilot | Production | Perform comprehensive validation and testing of AI models, ensuring adherence to healthcare compliance and reliability standards. Emphasize testing accuracy metrics for claims processing. *Acceptance Criteria:* • Validation meets predefined accuracy thresholds • All models pass compliance tests • Testing logs are complete and audit-ready *Associated Controls:* - [Model Reliability & Safety (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00030] - [Model Reliability & Safety (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00038] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002m7: | 18/Mar/26 12:00 AM | 10844 | CLAIMSPROC-4 | AI Validation & Testing | To Do | 05/Nov/25 4:40 PM
Deployment of AI Claims Processing Models | CLAIMSPROC-67 | 10965 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:40 PM | 05/Nov/25 4:40 PM | 05/Nov/25 5:33 PM |  | 18/Apr/26 12:00 AM | 0 | AI_Inventory | Pilot | Production | Deploy AI models into the production environment with considerations for robustness, security, and compliance. Ensure models integrate seamlessly with existing healthcare IT systems. *Acceptance Criteria:* • Deployment scripts execute without errors • Models integrate with existing IT systems • Post-deployment testing confirms operational readiness *Associated Controls:* - [Cyber Security (Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00036] - [Model Reliability & Safety (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00019] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002nr: | 03/Apr/26 12:00 AM | 10845 | CLAIMSPROC-5 | AI Deployment | To Do | 05/Nov/25 4:40 PM
RBAC Implementation for AI System Access | CLAIMSPROC-74 | 10979 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:40 PM | 05/Nov/25 4:40 PM | 05/Nov/25 5:33 PM |  | 04/May/26 12:00 AM | 0 | AI_Inventory |  | Production | Design and enforce Role-Based Access Control (RBAC) following the principle of least privilege across all AI systems, including data, APIs, and model registries. *Acceptance Criteria:* • RBAC policies defined for every AI component • Access limited based on job role and data sensitivity • Access violations logged and reviewed weekly • RBAC rules updated dynamically with org changes • PoLP validation performed quarterly *Associated Controls:* - [Authorization (RBAC) (Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00011] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002pb: | 19/Apr/26 12:00 AM | 10845 | CLAIMSPROC-5 | AI Deployment | To Do | 05/Nov/25 4:40 PM
AI Agent Identity and Action Attribution | CLAIMSPROC-80 | 10991 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:40 PM | 05/Nov/25 4:41 PM | 05/Nov/25 5:34 PM |  | 20/May/26 12:00 AM | 0 | AI_Inventory | Pilot | Production | Create unique identities for AI agents and establish mechanisms to trace each action to a specific agent or originating user through OAuth or equivalent tokenization methods. *Acceptance Criteria:* • All AI agents have unique machine identities • OAuth 2.0 On-Behalf-Of tokens used for attribution • Actions logged with origin and agent metadata • Agent identity integrated into centralized audit trail • Non-repudiation guaranteed through cryptographic signing *Associated Controls:* - [Agent Identity & Action Attribution (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00008] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002qn: | 05/May/26 12:00 AM | 10845 | CLAIMSPROC-5 | AI Deployment | To Do | 05/Nov/25 4:40 PM
Data-in-Transit Encryption Enforcement | CLAIMSPROC-86 | 11003 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:41 PM | 05/Nov/25 4:41 PM | 05/Nov/25 5:34 PM |  | 05/Jun/26 12:00 AM | 0 | AI_Inventory |  | Production | Mandate TLS 1.2+ encryption across all AI data exchanges, ensuring secure communication between APIs, model services, and infrastructure components. *Acceptance Criteria:* • All communications use TLS 1.2 or higher • Encryption validated through compliance scans • mTLS implemented for service-to-service communication • Certificates rotated automatically before expiry • Penetration testing verifies encryption strength *Associated Controls:* - [Data-in-Transit Encryption (Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00013] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002rz: | 21/May/26 12:00 AM | 10845 | CLAIMSPROC-5 | AI Deployment | To Do | 05/Nov/25 4:41 PM
Strong Authentication Mechanisms for AI Systems | CLAIMSPROC-92 | 11015 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:41 PM | 05/Nov/25 4:41 PM | 05/Nov/25 5:35 PM |  | 21/Jun/26 12:00 AM | 0 | AI_Inventory |  | Production | Implement MFA for all users and managed identities for inter-service authentication to prevent unauthorized access and impersonation across AI systems. *Acceptance Criteria:* • MFA enforced for all human access • Managed identities used for system-to-system communication • Authentication attempts logged and monitored • API keys rotated regularly • Access policies deny unauthorized attempts automatically *Associated Controls:* - [Authentication (Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00010] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002tb: | 06/Jun/26 12:00 AM | 10845 | CLAIMSPROC-5 | AI Deployment | To Do | 05/Nov/25 4:41 PM
Monitoring of AI Claims Automation System | CLAIMSPROC-98 | 11027 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:41 PM | 05/Nov/25 4:41 PM | 05/Nov/25 5:35 PM |  | 07/Jul/26 12:00 AM | 0 | AI_Inventory | Pilot | Production | Implement comprehensive monitoring of AI systems to track performance, system health, and compliance with regulatory standards. Include real-time alerts for anomaly detection. *Acceptance Criteria:* • Performance metrics are accurate and up-to-date • Alerts are triggered for any performance anomalies • Monitoring dashboard is accessible and user-friendly *Associated Controls:* - [Transparency & Explainability (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00023] - [Human Oversight (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00021] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002un: | 22/Jun/26 12:00 AM | 10846 | CLAIMSPROC-6 | AI Monitoring | To Do | 05/Nov/25 4:41 PM
Continuous Model Monitoring and Drift Detection | CLAIMSPROC-105 | 11041 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:41 PM | 05/Nov/25 4:41 PM | 05/Nov/25 5:36 PM |  | 23/Jul/26 12:00 AM | 0 | AI_Inventory | Pilot | Production | Implement continuous monitoring of data and model outputs to detect drift, anomalies, and performance degradation. Automate alerting and retraining workflows. *Acceptance Criteria:* • Model and data drift detection metrics in place • Automated alerts trigger retraining workflows • Monitoring dashboards track performance KPIs • Bias and anomaly reports reviewed regularly • All alerts logged with timestamps and resolution status *Associated Controls:* - [Model & Data Monitoring (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00020] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002w7: | 08/Jul/26 12:00 AM | 10846 | CLAIMSPROC-6 | AI Monitoring | To Do | 05/Nov/25 4:41 PM
Model Monitoring Review Frequency and KRI Response Framework | CLAIMSPROC-111 | 11053 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:41 PM | 05/Nov/25 4:41 PM | 05/Nov/25 5:36 PM |  | 08/Aug/26 12:00 AM | 0 | AI_Inventory |  | Production | Define and enforce a review frequency for continuous Model & Data Monitoring feeds, ensuring timely KRI response to detected anomalies or drift. *Acceptance Criteria:* • Model & Data Monitoring feeds have defined review frequencies • Automated reminders generated for overdue reviews • KRI thresholds linked to drift detection dashboards • All reviews logged and traceable • Daily monitoring cadence validated in audits *Associated Controls:* - [Model & Data Monitoring (Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00037] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002xj: | 24/Jul/26 12:00 AM | 10846 | CLAIMSPROC-6 | AI Monitoring | To Do | 05/Nov/25 4:41 PM
Governance Framework for AI Claims Processing | CLAIMSPROC-117 | 11065 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:41 PM | 05/Nov/25 4:41 PM | 05/Nov/25 5:36 PM |  | 24/Aug/26 12:00 AM | 0 | AI_Inventory | Pilot | Production | Establish a governance framework that outlines policies for responsible AI use, ensuring compliance with ethical and legal standards. Include protocols for updating procedures as regulations change. *Acceptance Criteria:* • Governance policies are documented and approved • Framework adapts to regulatory changes • Regular audits to ensure policy adherence *Associated Controls:* - [Fairness and Ethics (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00007] - [Data Privacy (Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00032] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i002yv: | 09/Aug/26 12:00 AM | 10847 | CLAIMSPROC-7 | AI Enterprise Governance | To Do | 05/Nov/25 4:41 PM
AI Governance Policy Final Approval Workflow | CLAIMSPROC-124 | 11079 | Story | To Do | CLAIMSPROC | CLAIMSPROC | software | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Fusefy Project for managing tasks | Medium |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | 05/Nov/25 4:41 PM | 05/Nov/25 4:41 PM | 05/Nov/25 5:37 PM |  | 09/Sep/26 12:00 AM | 0 | AI_Inventory | Pilot | Production | Establish a policy governance workflow ensuring AI Policy for PHI handling undergoes formal stakeholder review and approval before progressing to next lifecycle stages. *Acceptance Criteria:* • AI policy drafts undergo stakeholder review • Formal approval required before advancement • Audit logs track policy version, approver, and timestamp • Governance workflows integrated into AI documentation systems • Stage 1 completion contingent upon policy approval *Associated Controls:* - [KCI (Pilot, Production)¦https://fusefy-workshop.atlassian.net/jira/apps/316532c0-8e84-468f-8ca9-9a0727562348/cf06a7de-461c-4a34-b235-d86547366079/controls/view/AI-CTRL-00034] |  | Dinesh Kumar V | 712020:228632de-e1a3-4b1f-a505-5dfd41a77eea | [8 empty] | CLAIMSPROC-8 |  | 0¦i0030f: | 25/Aug/26 12:00 AM | 10847 | CLAIMSPROC-7 | AI Enterprise Governance | To Do | 05/Nov/25 4:41 PM